## Hospital Expansion Master
WBS Code | Activity Description | Status | Orig Dur (d) | Phys % Comp | Budget (BAC) | Planned (PV) | Earned (EV) | Actual (AC) | SPI | CPI
1 | HOSPITAL EXPANSION & CLINICAL CENTER | Active | 240 | 33.3% | 2500000 | 1200000 | 832500 | 950000
1.1 | Engineering & Detailed Design | Complete | 40 | 100% | 200000 | 200000 | 200000 | 195000
1.1.1 | Architectural Concept & Layouts | Complete | 20 | 100% | 100000 | 100000 | 100000 | 95000
1.1.2 | Structural Calculations & BIM Model | Complete | 15 | 100% | 60000 | 60000 | 60000 | 60000
1.1.3 | MEP Engineering Specifications | Complete | 20 | 100% | 40000 | 40000 | 40000 | 40000
1.2 | Procurement & Subcontracts | Active | 60 | 25% | 800000 | 400000 | 200000 | 250000
1.2.1 | HV Switchgear & Substation Package | Active | 60 | 25% | 500000 | 250000 | 125000 | 150000
1.2.2 | Chillers & AHU Packages | Not Start | 50 | 0% | 300000 | 150000 | 75000 | 100000
1.3 | Civil & Structural Works | Active | 100 | 40% | 900000 | 450000 | 360000 | 410000
1.3.1 | Site Excavation, Shoring & Dewatering | Active | 30 | 75% | 300000 | 250000 | 225000 | 240000
1.3.2 | Foundation Raft & Retaining Walls | Not Start | 40 | 0% | 400000 | 100000 | 50000 | 70000
1.3.3 | Superstructure Concrete Pour | Not Start | 60 | 0% | 200000 | 100000 | 85000 | 100000
1.4 | MEP & Interior Fitout | Not Start | 40 | 0% | 400000 | 100000 | 50000 | 65000
1.5 | Testing, Commissioning & Handover | Not Start | 25 | 0% | 200000 | 50000 | 22500 | 30000

## S-Curve Progress
Month | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC)
Jan-26 | 100000 | 95000 | 90000
Feb-26 | 250000 | 240000 | 235000
Mar-26 | 480000 | 420000 | 460000
Apr-26 | 750000 | 630000 | 710000
May-26 | 1200000 | 832500 | 950000
Jun-26 | 1650000
Jul-26 | 2100000
Aug-26 | 2500000

## DCMA 14-Point Report
Metric # | DCMA Check Description | Target Threshold | Actual Score | Compliance Status
1 | Logic (Missing Predecessor or Successor) | <= 5% | 36.36% | FAIL
2 | Leads (Negative Lags) | 0% | 0.00% | PASS
3 | Lags (Positive Lags > 0) | <= 5% | 0.00% | PASS
4 | Relationship Types (Finish-to-Start Preference) | >= 90% FS | 100.00% | PASS
5 | Hard Constraints | <= 5% | 0.00% | PASS
6 | High Float (> 44 Working Days) | <= 5% | 0.00% | PASS
7 | Negative Total Float | 0% | 72.73% | FAIL
8 | High Duration (> 44 Working Days) | <= 5% | 27.27% | FAIL
9 | Invalid Dates Integrity | 0% | 0.00% | PASS
10 | Resource Assignment Loading | 100% Loaded | 100.00% | PASS
11 | Missed Tasks (Execution vs Baseline Finish) | <= 5% | 0.00% | PASS
12 | Critical Path Integrity Test | Continuous | Pass (Continuous) | PASS
13 | Critical Path Float Consumption Index (CAPI) | 0.95 - 1.05 | 1.00 | PASS
14 | Baseline Execution Index (BEI) | >= 0.95 | 1.00 | PASS

## 4-Week Lookahead
Activity ID | Activity Name | Early Start | Early Finish | Remaining Dur | Total Float | Assigned Resource | Status
HV-101 | HV Switchgear Delivery & Rigging | 01-Jun-26 | 20-Jun-26 | 15d | 0d | Electrical Crew A | In Progress
HV-102 | Transformer Substation Cable Pulling | 10-Jun-26 | 30-Jun-26 | 15d | 0d | Subcontractor - High Voltage | In Progress
CIV-201 | Excavation Zone B Deep Pit | 01-Jun-26 | 15-Jun-26 | 10d | 5d | Earthmoving Plant #3 | In Progress
CIV-202 | Retaining Wall Shoring & Anchoring | 16-Jun-26 | 30-Jun-26 | 12d | 5d | Specialist Piling Contractor | Planned