## PROJECT
proj_id | proj_short_name | plan_start_date | plan_end_date | scd_end_date
101 | HOSPITAL_EXPANSION | 2026-01-05 08:00 | 2026-12-31 17:00 | 2026-12-31 17:00

## PROJWBS
wbs_id | proj_id | parent_wbs_id | wbs_short_name | wbs_name | seq_num
1 | 101 |  | 1 | Hospital Expansion Project | 10
2 | 101 | 1 | 1.1 | Engineering & Design | 20
3 | 101 | 1 | 1.2 | Procurement & Subcontracts | 30
4 | 101 | 1 | 1.3 | Civil & Structural Works | 40
5 | 101 | 1 | 1.4 | MEP & Interior Fitout | 50
6 | 101 | 1 | 1.5 | Testing & Commissioning | 60

## TASK
task_id | proj_id | wbs_id | task_code | task_name | task_type | status_code | target_durn_hr_cnt | remain_durn_hr_cnt | target_work_qty | remain_work_qty | act_work_qty | total_float_hr_cnt | target_start_date | target_end_date | act_start_date | act_end_date
10 | 101 | 2 | A1000 | Architectural Concept & Layouts | TT_Task | TK_Complete | 160.0 | 0.0 | 200 | 0 | 200 | 0.0 | 2026-01-05 08:00 | 2026-01-30 17:00 | 2026-01-05 08:00 | 2026-01-30 17:00
11 | 101 | 2 | A1010 | Structural Foundation Calculations | TT_Task | TK_Complete | 120.0 | 0.0 | 150 | 0 | 150 | 0.0 | 2026-02-02 08:00 | 2026-02-20 17:00 | 2026-02-02 08:00 | 2026-02-20 17:00
12 | 101 | 2 | A1020 | MEP Detailed Engineering Specs | TT_Task | TK_Active | 160.0 | 40.0 | 180 | 45 | 135 | 16.0 | 2026-02-02 08:00 | 2026-02-27 17:00 | 2026-02-02 08:00
13 | 101 | 3 | A1030 | Procure High-Voltage Switchgear | TT_Task | TK_NotStart | 480.0 | 480.0 | 500 | 500 | 0 | 40.0 | 2026-03-02 08:00 | 2026-05-29 17:00
14 | 101 | 3 | A1040 | Procure Chillers & AHUs | TT_Task | TK_NotStart | 400.0 | 400.0 | 450 | 450 | 0 | 80.0 | 2026-03-02 08:00 | 2026-05-15 17:00
15 | 101 | 4 | A1050 | Site Excavation & Shoring | TT_Task | TK_Active | 240.0 | 80.0 | 300 | 100 | 200 | -40.0 | 2026-02-23 08:00 | 2026-04-03 17:00 | 2026-02-23 08:00
16 | 101 | 4 | A1060 | Foundation Raft & Retaining Walls | TT_Task | TK_NotStart | 320.0 | 320.0 | 400 | 400 | 0 | -40.0 | 2026-04-06 08:00 | 2026-05-29 17:00
17 | 101 | 4 | A1070 | Superstructure Concrete Pour | TT_Task | TK_NotStart | 480.0 | 480.0 | 600 | 600 | 0 | -40.0 | 2026-06-01 08:00 | 2026-08-28 17:00
18 | 101 | 5 | A1080 | Interior Partitions & Flooring | TT_Task | TK_NotStart | 320.0 | 320.0 | 350 | 350 | 0 | -40.0 | 2026-08-31 08:00 | 2026-10-23 17:00
19 | 101 | 5 | A1090 | MEP First & Second Fix | TT_Task | TK_NotStart | 320.0 | 320.0 | 350 | 350 | 0 | -40.0 | 2026-08-31 08:00 | 2026-10-23 17:00
20 | 101 | 6 | A1100 | Integrated System Testing | TT_Task | TK_NotStart | 200.0 | 200.0 | 250 | 250 | 0 | -40.0 | 2026-10-26 08:00 | 2026-11-27 17:00
21 | 101 | 6 | A1110 | Authority Inspection & Handover | TT_FinMile | TK_NotStart | 0.0 | 0.0 | 0 | 0 | 0 | -40.0 | 2026-11-30 17:00 | 2026-11-30 17:00
22 | 101 | 4 | A1055 | Underground Dewatering Scope Addition | TT_Task | TK_Active | 80.0 | 40.0 | 100 | 50 | 50 | -40.0 | 2026-03-01 08:00 | 2026-03-15 17:00 | 2026-03-01 08:00

## TASKPRED
task_pred_id | task_id | pred_task_id | pred_type | lag_hr_cnt
1001 | 11 | 10 | PR_FS | 0.0
1002 | 12 | 10 | PR_FS | 0.0
1003 | 15 | 11 | PR_FS | 0.0
1004 | 16 | 15 | PR_FS | 0.0
1005 | 17 | 16 | PR_FS | 0.0
1006 | 18 | 17 | PR_FS | 0.0
1007 | 19 | 17 | PR_FS | 0.0
1008 | 20 | 18 | PR_FS | 0.0
1009 | 20 | 19 | PR_FS | 0.0
1010 | 21 | 20 | PR_FS | 0.0
1011 | 13 | 12 | PR_FS | 0.0
1012 | 14 | 12 | PR_FS | 0.0
1014 | 16 | 22 | PR_FS | 0.0